## Components
Sai Avighna Dental Clinic |  |  |  | Sub-Page/Form | [5 empty] | Status
Phase I |  |  | Design | [7 empty] | Estimated Person Days | Date 1 (2 person)
| 1.1 |  | Database Design | [7 empty] | 1 | 2020-09-15
| 1.2 |  | App Design | [7 empty] | 1 | 2020-09-16
| 1.3 |  | Infrastructure setup | [7 empty] | 2 | 2020-09-18
[5 empty] | Admin | General User | Doctor | Receptionist | Other
Phase II
| 2.1 |  | Forms
| 2.1.1 | App | Login Page | [7 empty] | 2 | 2020-09-22
| 2.1.2 | App | New Patient entry/Edit Patient entry | [7 empty] | 2 | 2020-09-24
| 2.1.3 | App | Medical History | Consultation | [6 empty] | 2 | 2020-09-26
| 2.1.4 | App | Dental Chart | Consultation | [6 empty] | 2 | 2020-09-28
| 2.1.5 | App | Dental Treatment | Consultation | [6 empty] | 2 | 2020-09-30
| 2.1.6 | App | Notes | Consultation | [6 empty] | 2 | 2020-10-02
| 2.1.7 | App | Lab Test | Consultation | [6 empty] | 2 | 2020-10-04
| 2.1.8 | App | Consent uploads | Consultation | [6 empty] | 1 | 2020-10-06
| 2.1.9 | App | Treatment | Consultation | [6 empty] | 2 | 2020-10-07
| 2.1.10 | App | Referrals | Consultation
| 2.1.11 | App | Billing | Consultation | [6 empty] | 2 | 2020-10-09
| 2.1.12 | App | Summary | Consultation | [6 empty] | 2 | 2020-10-11
| 2.1.13 | App | New Doctor | [7 empty] | 2 | 2020-10-13
| 2.1.14 | App | Add Medicine/Add Treatment/Create logins etc., | [7 empty] | 2 | 2020-10-15
| 2.1.15 | Website | Book Appointment | [7 empty] | 2 | 2020-10-17
Phase III | 3.1 |  | Pages
| 3.1.1 | App | Appointments | [7 empty] | 2 | 2020-10-19
| 3.1.2 | App | Patients List (searchable) | [7 empty] | 2 | 2020-10-23
| 3.1.3 | App | Dashboard | [7 empty] | 2 | 2020-10-25
| 3.1.4 | App | Past Records of a Patient | Consultation | [6 empty] | 2 | 2020-10-27
| 3.1.5 | App | Team of Doctors
| 3.1.6 | App | Communications
| 3.1.7 | Website | Main Page -- About | [7 empty] | 2 | 2020-10-29
| 3.1.8 | Website | List of Doctors | [7 empty] | 2 | 2020-10-31
Phase IV | 4.1 |  | Functions
| 4.1.1 |  | Styling & Logo | [7 empty] | 2 | 2020-11-04
| 4.1.2 |  | CSS | [7 empty] | 2 | 2020-11-06
| 4.1.3 |  | Testing with Users | [7 empty] | 2 | 2020-11-08
| 4.1.4 |  | Go-Live | [7 empty] | 2 | 2020-11-12
47
Formulas:
Date 1 (2 person) = SUM([Date 1 (2 person), row above]+[Estimated Person Days])
Date 1 (2 person) = ([Date 1 (2 person), row above]+[Estimated Person Days, row above])

## Appointments
Functions | sub-Functions | Conditions | Links
Book an appointment |  |  | Appointment Page main Create new Patient
Opens the appointments for the given day. | Cancel Appointments |  | Consultation Page
Should also show appointments of other days
Should also allow to start a walk-in consultation |  | New or Old patient? | Register Page

## Consultation
Functions | sub-Functions | Conditions | Links
Past Records | Summary Reports
Medical History
Dental Chart
Dental Treatments
Notes
Lab Test
Consents
Treatment
Referrals | ??? | ??? | ???
Billing
Summary

## New Edit Patient
Functions | sub-Functions | Conditions | Links
Create/Update Patient |  |  | Upcoming Appointments New Appointment Consultations

## Team of Doctors
Functions | sub-Functions | Conditions | Links
Doctor's profile |  |  | Appointments Book Appointment
List of Doctors